## Sheet1
Topic | Task Name | Start Date | End Date | Completion % | Status | Hidden | Project | Employee | Week | Milestone_Text | Milestone_Author_Name | Milestone_Role
Topic 1 | other tasks | 2026-04-22 | 2026-04-24 | 0 | Planned | FALSE | Other | Employee 1 | 1 | -- | Administrator | Admin
Robot | Robot placement Robot reach Dcs zone IIC Singularly In progress Cycle time optimisation Programming zone Logic's DCS for Conveyor Created in Bottom Position Retract Point for Conveyor with DCS in Top Position (Front Pick - Singularity , Position Not Reachable Error) Retract Point(Placing Point ) for Conveyor with Variable Height for Front Pick Retract Point for (Placing Point )Conveyor with Variable Height for Bottom Pick Front Pick Trigger Point for 3 Rows (Individual) Front Pick Trigger Point for 5 Rows (Individual) Front Pick Trigger Point for 5th Row (2 Trigger) DCS Zone for Container Communication Between Robot and PLC. Gi Assigned for X,Y,Z Co-ordinates from PLC Gi Assigned for Height & Width Co-ordinates from PLC Gi Assigned for Row & Column for Full Snap Gi Assigned for Row & Column for Each Snap Full Trail Taken with Container DCS Full Row Trail Taken with X,Y,Z Co-ordinates IIC Interconnect to Slave (Trail) Trail Taken for Top Pick Inside the Container Trail Taken for Bottom Pick Inside the Container Program Updation with Top Fully Stacked or Not Trigger Auto Run IO Configuration Update Dual robot IO Logic Updation in Robot | 2026-03-30 | 2026-04-04 | 70 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 | nan | Administrator | Admin
Vision System | Camera selection. Other technology tested Camera placement Camera calibration Processing time optimisation Code for X,Y,Z Co-ordinates Code for w,p,r Co-ordinates Bounding Box Logic Created Center Point of the Box Logic Created Capture Trigger Logic Created Co-ordinate send Logic Created Segmentation Logic Created Length & Width Logic created Rows & Columns Logic created Trail Taken with X,Y,Z Co-ordinates in Vision PLC Logic For X,Y,Z and Capture Trigger Height & Width Logic Created In progress: Dataset creation Logic's Layers in code Sorting Logic Created in Python Communication with PLC Zone for Robot - 1 & 2 in Python (Trail) Depth Calibration in Vision Trail Taken with Length & Height Co-ordinates in Vision Trail Taken with Row and Column Co-ordinates in Vision Full Snap Trigger Logic Created Number of Rows and Columns & Count for Full Snap Created Number of Rows and Count in Each Row Logic Created | 2026-03-30 | 2026-04-05 | 60 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
AGV | Dimensions fixed Speed, accuracy, stopping fixed Tel operation using Joystick completed Container initial phase trial completed full container trail yet to make container detection | 2026-04-14 | 2026-04-21 | 80 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
EOAT | Different types explored weight optimised Robot self hindrance defined Square EOAT tested load testing speed testing carton box testing solenid testing ss eoat testing alu eoat testing chamber testing designing of optimal eoat designing of eoat with inbuilt camera designing of various chamber eoat suitable for both vacuum generator and blower desining of maching eoat designing of fully machining OEM ref eoat Rectangular eoat with cups on sheet,( modular ) Rectangular yet to test | 2026-04-14 | 2026-04-21 | 90 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
Vacuum System | Generator and Blower tested Flow & Power calculation done Different cups & no.of cups tested Cups arragement and diameter fixed cup dia confirmation vacuum generator flow confirmation vacuum generator input confirmation vacuum vs blower vacuum cupmaterial confirmation 1 vs 2 vs 3 vs 4 generator dependancy vacuum cup brand confirmation Solenoid Partition | 2026-04-14 | 2026-04-21 | 90 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
Conveyor and Scissor lift | Concept planned Conveyor design Scissor lift dimension Sensor placement Conveyor/scissor logic Auto mode testing | 2026-04-14 | 2026-04-21 | 85 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
Container | Different size of container explained Inside and outside and base tested and measured. | 2026-04-14 | 2026-04-21 | 75 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
Objects | Different types of boxes tested and explained Damaged and other boxes yet to trial | 2026-04-14 | 2026-04-21 | 25 | Completed | FALSE | Truck Unloading Project | Unassigned | 14 |  | Administrator | Admin
Robot | OS-144 Error (SPNX ERROR) Loop logic Error Faced Loop Logic Creation for both (camera and robot ) logic OS_144 error (under automation Fanuc spnx internal spnx client base) I/O logic (DI signal clash and signal reading problem). Sorting logic change depending on the face regarding face using robot base not camera. | 2026-04-06 | 2026-04-12 | 2 | Completed | FALSE | Truck Unloading Project | Unassigned | 15 |  | Administrator | Admin
Vision System | Face detection (80% completed ) I/O logic communication sorting fine tuning loop logic | 2026-04-06 | 2026-04-12 | 5 | Completed | FALSE | Truck Unloading Project | Unassigned | 15 |  | Administrator | Admin
Dataset | Dataset collection and process | 2026-04-24 | 2026-05-30 | 1 | Planned | FALSE | Truck Unloading Project | Unassigned | 17 |  | Administrator | Admin
Robot | -- | 2026-04-28 | 2026-05-30 | 72 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 1 |  | Varshetha | Employee
Vision System | -- | 2026-04-28 | 2026-05-30 | 65 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 1 |  | Varshetha | Employee
Conveyor and Scissor lift | -- | 2026-04-28 | 2026-05-05 | 50 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 1 |  | Administrator | Admin
AGV | -- | 2026-04-28 | 2026-05-05 | 80 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
EOAT | -- | 2026-04-28 | 2026-05-30 | 90 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
Vacuum System | -- | 2026-04-28 | 2026-05-05 | 90 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
Container | -- | 2026-04-28 | 2026-05-05 | 75 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
Dataset | -- | 2026-04-28 | 2026-05-30 | 1 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
Objects | -- | 2026-04-28 | 2026-05-30 | 25 | Planned | FALSE | Truck Unloading Project-Concept-1(Single Robot) | Unassigned | 5 |  | Administrator | Admin
Robot | -- | 2026-04-28 | 2026-05-05 | 10 | Planned | FALSE | Truck Unloading Project_Concept-2 (Dual Robot) | Unassigned | 5 | IIC & Logics Need to be Done | Administrator | Admin
EOAT | -- | 2026-04-28 | 2026-05-30 | 90 | Planned | FALSE | Truck Unloading Project_Concept-2 (Dual Robot) | Unassigned | 5 |  | Administrator | Admin
Vision System | -- | 2026-04-28 | 2026-05-30 | 50 | Planned | FALSE | Truck Unloading Project_Concept-2 (Dual Robot) | Unassigned | 5 |  | Administrator | Admin