## Sheet1
Task ID | PM | Project Number | Assigned Date | Station Name | Task Name | Assignee Email | Responsible Person | Department | Due Date | Planned Hrs | Planned % Completion | Actual Hrs | Actual % Completion | Status | Re Shd | Remarks | Proof Link | Deviation % in Completion | Escalation to Hr Management | Time Stamp | Task Completion Approval Status from HOD | Task Completion Non Approval Status from HOD | HOD REMARKS | Uninformed Leave | Notification Sent | Task Completion Approval Status from PMT | Task Completion Non Approval Status from PMT | PMT Remarks | Hrs Deviation | Task Approval Status
1039 | SUDHARSAN | R&D | 2026-04-08 08:00 |  | Dashboard creation for weekly update | efficard5@gmail.com | Gowtham-R&D | R&D | 4/8/2026 16:30:00 | 2 | 100 | 0 | 0 | FALSE | FALSE
1040 | SUDHARSAN | R&D | 2026-04-08 08:00 |  | Animation creation using antigravity check | efficard5@gmail.com | Gowtham-R&D | R&D | 4/8/2026 16:30:00 | 3 | 100 | 0 | 0 | FALSE | FALSE
1041 | SUDHARSAN | R&D | 2026-04-08 08:00 |  | Brush carry forward in R&d system | efficard5@gmail.com | Gowtham-R&D | R&D | 4/8/2026 16:30:00 | 2 | 100 | 0 | 0 | FALSE | FALSE
1042 | SUDHARSAN | R&D | 2026-04-08 08:00 |  | Dataset creation using roboflow - Flowchart for it | efficard5@gmail.com | Gowtham-R&D | R&D | 4/8/2026 16:30:00 | 1 | 100 | 0 | 0 | FALSE | FALSE
1043 |  |  | 2026-04-08 08:00 | [5 empty] | 04/10/2026 16:30:00 | 2 | 100 | 0 | 0 | FALSE | FALSE |  |  |  | FALSE | 04/08/2026 11:17:54 |  |  |  | FALSE | FALSE |  |  |  |  | Pending
1044 | Sudharsan | RD001 | 2026-04-08 08:00 |  | Vision dataset | efficard5@gmail.com | Bharat |  | 04/10/2026 16:30:00 | 2 | 100 | 0 | 0 | FALSE | FALSE |  |  |  | FALSE | 04/08/2026 11:19:00 |  |  |  | FALSE | FALSE |  |  |  |  | Pending
1045 | Sudharsan | RD001 | 04/08/2026 08:00:00 |  | Vision dataset | efficard5@gmail.com | Bharat |  | 04/10/2026 16:30:00 | 2 | 100 |  |  | FALSE | FALSE |  |  |  | FALSE | 04/08/2026 11:19:05 |  |  |  | FALSE | FALSE |  |  |  |  | Pending